## How to use
Voxistics scope (MoSCoW)
Horizon (edit this): the next playable build -- a world you can build in, decorate and hear, with item logistics decided.
Must -- the horizon fails without it.
Should -- important, but the horizon still works without it.
Could -- nice to have if it's cheap; first to drop.
Won't -- not this horizon (parked, not rejected). The dev pile lives here.
How we use it
1. Before new work starts, it needs a row here. New ideas enter as Could or Won't unless the owner says otherwise.
2. Only the owner sets Must. Claude's suggestions say 'Claude (proposed)' in Decided by until the owner decides.
3. Priority and Status are drop-downs; Summary counts update by themselves.
4. Add a row at the bottom of Scope with the next ID (S040, S041, ...). Example: S040 ¦ Audio ¦ Footstep volume option ¦ Could ¦ Not started ¦ Only if footfalls stay ¦ 10.4 ¦ Owner
5. When a horizon ships, move its Won'ts up for review and set a new horizon above.

## Scope
ID | Area | Item | Priority | Status | Notes / boundary | Design ref | Decided by
S001 | Engine | Chunked world, streaming, eviction, regeneration | Must | Done |  | Part II | Owner
S002 | Engine | Save/load: slots, autosave, backups, settings file | Must | Done |  | Part VII | Owner
S003 | Engine | Native tests + frame profiler (F3) | Must | Done | Every change keeps tests at zero failures | Parts XVI-XVII | Owner
S004 | Engine | Lagless rule: cost scales with what's on screen or changing | Must | In progress | Standing rule, never 'done' | CLAUDE.md | Owner
S005 | Engine | Release-build performance check on the owner's PC | Should | Not started | The Ctrl+F3 report tool exists (perf_report.txt); running the check awaits the owner | Part XVI | Claude (proposed)
S006 | Blocks & art | Block registry, shapes, 32 px materials with normal/shine/glow maps | Must | Done | 32 px chosen by owner | 4.3, 4.13 | Owner
S007 | Blocks & art | Natural, dark, genesis and custodian material sets | Must | Done |  | 4.3 | Owner
S008 | Blocks & art | Plant cards | Must | Done |  | 4.14 | Owner
S009 | Blocks & art | Faceted props + dwelling/industry pieces (40 blocks) | Must | Done | In the library only, not world gen yet | 4.15 | Owner
S010 | Blocks & art | Try the library out in the landscape | Must | In progress | Owner play-test; decides names and what stays | 4.15 | Owner
S011 | Blocks & art | Name pass over all blocks | Should | Not started | After the landscape try-out | Part VIII | Owner
S012 | Blocks & art | Landmark shapes: canopy cap, coil stalk | Could | Done | Glowcap, moss canopy, fern coil, sprout coil in the library | 4.15 | Owner
S013 | Blocks & art | Parked decorative set: stained glass, porcelain floral, rune shrine | Won't | Parked | Dev pile; not this horizon | Part XX | Owner
S014 | World | World / biome generation using the library blocks and props | Should | Not started | 'Coming in the pipeline'; not started | Part II | Owner
S015 | Rendering | Lighting, shadows, atmosphere, clouds, bloom, see-through blocks, glow light | Must | Done |  | 4.8-4.12 | Owner
S016 | Rendering | Soft filtering / colour bleed / large-scale variation comparison | Could | Done | Owner picked D; colour bleed dropped after the playtest (halo). Variation + distance filtering kept (4.16) | Part XX | Owner
S017 | Gameplay | Movement: sprint, crouch, power slide | Must | Done |  | 4.7 | Owner
S018 | Gameplay | Block library + 10-slot hotbar | Must | Done |  | 4.3 | Owner
S019 | Gameplay | Debug time control (F8, [ ]) | Must | Done |  | Part XV | Owner
S020 | Industry | Item logistics: pulse through pipes | Must | In progress | Built: harvester at a constant rate (faster under The Line); plain/clockwise/anticlockwise pipes give pulse spin; networks share out to stores (unlimited) and the machine; open ends fire straight, facing mouths catch; store view with bead heaps. Open: what harvesters draw from, what pulse becomes. | Part VI | Owner
S021 | Industry | First working machine (the placeholder becomes real) | Should | Not started | Core of the factory game. Logistics decided (pulse); waits on what pulse becomes / how it is burned | Part VI | Claude (proposed)
S022 | Industry | Byproducts and land health (industry safe when well run) | Won't | Parked | Dev pile; core direction but not this horizon | Part XX | Owner
S023 | Industry | Essence as a transmutation economy | Could | Not started | Candidate direction only | Part XIX | Claude (proposed)
S024 | Threat | Ooze rifts born of neglect | Won't | Parked | Dev pile | Part XX | Owner
S025 | Simulation | Fluids | Won't | Parked | Dev pile; heavy | Part XX | Owner
S026 | Simulation | Vapours and gases | Won't | Parked | Dev pile; heavy | Part XX | Owner
S027 | Simulation | Plants drop when their support is removed | Won't | Parked | Dev pile | Part XX | Owner
S028 | Audio | Day-cycle music (one clock) | Must | Done |  | Part XIV | Owner
S029 | Audio | World sound palette + three soundscape axes | Must | Done | Owner finds it plain; develop later | 10.4 | Owner
S030 | Audio | Develop the palette's character further | Could | Not started | When the game's direction is clearer | 10.4 | Owner
S031 | Audio | Machine sounds react to the placeholder machine | Must | Done | Online on placing; hum and rhythm near machines | 10.4 | Owner
S032 | Audio | Positional (stereo) sound | Could | Done | Owner: go ahead. Placed sounds pan, ping-pong echo, Mono audio toggle | 10.3 | Owner
S033 | Audio | Sounds waiting on systems: mending, rift closed, rift omens | Won't | Parked | Built and tested; nothing triggers them yet | 10.4 | Claude (proposed)
S034 | The Line | The Line prototype: travelling pivot, clockwise spin, time expression | Must | Done | Playtest fixes: pivot now lands on the spot you actually spend time in x and z (16-block cells remembering where their time was spent; 30-min half-life). Expression (owner's pick): the visible sky races ahead near the line and runs slow after you leave; sun and light keep the real clock; wobble kept faint. | Part XVIII | Owner
S035 | The Line | Hide the debug marker once the sky effect is signed off | Should | Not started |  | Part XVIII | Claude (proposed)
S036 | The Line | Player structures as extra pivot sources | Could | Not started | Owner expected the essence attractor to do this; today it doesn't (it only draws from convergence zones). Owner to decide whether attractors should pull The Line's pivot. | Part XVIII | Claude (proposed)
S038 | Standing rules | Nothing anyone owns: no brands, currencies, crypto, borrowed art or names | Must | In progress | Standing rule | Part VIII | Owner
S039 | Standing rules | Photosensitivity: nothing flashes more than 3 times a second | Must | In progress | Standing rule | Part XI | Owner
S040 | Audio | Vocal ad-libs and footfalls | Must | Done | Owner: keep | 10.4 | Owner
S041 | Audio | 'Unveil' cue on first placement of a block type | Won't | Parked | Owner: nixed; the recipe stays unused | 10.4 | Owner
S042 | Audio | Footsteps on the beat, by gait and ground hardness | Must | Done | Crouch/walk/sprint; soft scuffs, hard knocks in key | 10.4 | Owner
S043 | World | Default plain as a fractal patchwork of three ground materials | Must | Done | Grass / sand / pebbles by feel underfoot; flat v2; materials swappable | Part II | Owner
S044 | UI | Buttons that look and feel pressable (mechanical press cue) | Must | Done | Keys act on release; sliders are beads on a string | Part XII | Owner
S045 | Standing rules | Privacy: no telemetry, crash reporting or hardware reading; target a modest old Windows PC | Must | In progress | Standing rule | CLAUDE.md | Owner
S046 | Crafting | Crafting system brainstorm: gathering, representation, uses, advancement from the natural surroundings | Should | Not started | After the playtest. Seed: microbes/germs gathered as essence, coloured/'flavoured' by the source's biological makeup. Owner to confirm priority. | Part XX | Owner
S047 | Playtest fixes | Footsteps louder; fog haze + distance filtering; midday hitch (music slices, sliced shadow redraw) | Must | Done | From the first playtest on the owner's rig | 4.8, 4.16, 14.7 | Owner
S048 | Gameplay | Forgiving power-slide timing; faster sprint (7.5) | Must | Done | Crouch/sprint in either order within 0.3-0.4 s | 4.7 | Owner
S049 | Rendering | Frame rate limit 30-200 (default 60) and vsync toggle | Must | Done | Graphics settings | 12.y | Owner
S050 | Gameplay | Breaking blocks: how it is done, and with what tools (if any) | Could | Parked | Owner: comes later, once we decide what tools there are. Today a click breaks a block instantly. Priority is the owner's to set. | Part XX | Claude (proposed)
S051 | Rendering | Pre-generated fracture: a broken block splits into pieces that tumble and settle | Could | Parked | Owner's idea, for with S050. Cheap by design: fracture patterns baked once per shape (a handful of variants), a few short-lived pieces per break, no per-block data. Nothing flashes. | Part XX | Claude (proposed)
S052 | UI | Translation / language packs | Won't | Not started | Owner: not a priority; English only, kept minimal so non-native speakers pick it up through play. Estimate if ever wanted: Latin scripts a few days (string table, accented glyphs); CJK needs a glyph cache. | — | Owner
S053 | Art | A big new batch of library blocks to sort through | Should | Not started | Owner isn't thrilled with the current set; wants a large pile to choose from. | 4.13, 4.15 | Owner
S054 | Review | Reviews: music fit; optimisation and architecture; texture library direction | Should | Not started | Owner asked for a distanced look at each | — | Owner
S055 | Industry | Pulse spin: three pipe kinds, spin carried and counted | Must | Done | Owner's idea; seen as corkscrew comets in the air and heaps by colour in stores | 6.0 | Owner
S056 | World | Fliers: two-winged day-lived creatures that fly low; the line ages them | Should | Not started | Owner's idea. Die after one game day or sooner under The Line; death makes grass glow vividly for a while, or grows mold on dirt/wood | — | Owner
S057 | World | Mold that sprouts a mushroom after a game day or after rain | Could | Not started | Owner's idea; rain needs a weather system (to discuss) | — | Claude (proposed)
S058 | World | Covered grass turns to dirt (not overnight) | Should | Not started | Deprived of sky, not of daylight | Part V | Owner
S059 | World | Weather (rain first) | Could | Not started | Owner: yet to discuss | — | Claude (proposed)
S060 | The Line | The Line grows to a plane with the player's power and influence | Won't | Not started | Owner: low priority, discuss later | Part XVIII | Owner
S061 | Industry | Diffuser: spends pulse widening The Line's band (the first loop) | Must | Done | Owner's design: feed per second keeps the band wide; harvesters above/below need it | 6.0, XVIII | Owner
S062 | UI | First-steps tutorial on a new world, skippable | Must | Done | One line at a time, moves on as done; Enter skips | 6.0 | Owner
S063 | Gameplay | New world starts with harvester, pipe, chest, diffuser on the hotbar | Must | Done |  | 6.0 | Owner
S064 | Accessibility | Colour-vision modes, one per kind of colour blindness | Should | Not started | Owner: red vs blue (pulse spin) must stay unmistakable for each kind. Spin already has non-colour cues (swirl, thread hand, bead turn, corkscrew) | 11.x | Owner
S065 | Industry | Machines sped up or slowed by time flux | Could | Not started | Owner: pipes and pulse in the air stay unaffected; harvesters are the first | 6.0 | Owner
Note on H1: Owner = decided by the owner. Claude (proposed) = a suggestion awaiting the owner's call: promote, demote or delete it.

## Summary
Scope at a glance
Counts update from the Scope sheet.
Priority | Done | In progress | Not started | Parked | Total | Done %
Must
Should
Could
Won't
Total
Open Musts (not done)
Proposals awaiting the owner